# MakeoverArena Digital Transformation — Project Status Report

Build Progress · Milestone Plan · Third-Party Integrations

SentinelAI Development Team

24 May 2026

# Executive Summary

MakeoverArena is a Nigerian study-abroad consultancy currently transforming from a manual Instagram/WhatsApp workflow into a fully automated digital platform. The project was scoped in a formal Product Requirements Document (PRD) dated 11 May 2026 with a 1-month delivery target.

As of this report, the platform is approximately 78% complete against the full PRD scope. The public-facing website, inquiry pipeline, email automation, AI chatbot, and admin dashboard are substantially built. The two critical remaining gaps are Paystack payment integration and document upload management — both explicitly required by the PRD.

This report covers:

- What has been built and is working

- What remains to be done

- A detailed 4-week plan to reach initial release

- A full audit of all third-party integrations and their current status

# 1. What Has Been Built

## 1.1 Technology Stack

| Layer | Technology | Version |
| --- | --- | --- |
| Framework | Next.js (App Router) | 16.2.1 |
| Language | TypeScript | 5.x |
| Styling | Tailwind CSS v4 + Radix UI | 4.x |
| Database | Supabase (PostgreSQL) | — |
| AI Chatbot | OpenAI GPT-4o-mini via AI SDK | v6 |
| Email | Resend + React Email | — |
| Booking | Cal.com embed + webhook | — |
| Rate Limiting | Upstash Redis | — |
| Validation | Zod v4 + react-hook-form | 4.x / 7.x |
| Deployment | Vercel (linked) | — |

## 1.2 Public Website (Marketing Pages)

All public-facing marketing pages are complete and production-ready:

- Homepage (/) — Hero section, stats bar (2,400+ students, 92% success rate), 4 service cards, 6 study destination country cards, testimonials, FAQ preview, and footer CTA

- About (/about) — Mission statement, 4 company values, 3 team member profiles, 6-milestone company timeline

- Services — Four dedicated service pages: Undergraduate, Graduate/Masters, Scholarships, and Visa Support — each with programme details, success statistics, and application CTAs

- Success Stories (/success-stories) — 6 student testimonial cards with country filters and scholarship badges

- FAQ (/faq) — Accordion-style FAQ grouped into 6 categories with live keyword search

- Book Consultation (/book) — Cal.com booking embed (renders live iframe when configured), office hours, contact methods

- Legal pages — Privacy Policy (10 sections), Terms of Service (10 sections), Cookie Policy (3 cookie types) with GDPR-compliant cookie consent banner

- Navbar — Responsive, transparent-on-homepage, active route highlighting, mobile hamburger menu

- Footer — 5-column layout with social links, service links, and legal links

## 1.3 Multi-Step Inquiry Form (/apply)

The student application form is fully operational:

- 5 steps covering: service selection → personal information → academic profile → study preferences → additional details

- Zod v4 validation on every field, per-step with Back/Next navigation

- localStorage draft save — progress is preserved if the browser is closed

- Rate limited — 5 submissions per hour per IP via Upstash Redis (graceful fallback if Redis unavailable)

- API route (POST /api/inquiries) — validates, inserts into Supabase, captures UTM parameters

- Email triggers — automatically sends confirmation to student and alert to admin on submission

- Success screen — shown after successful submission

## 1.4 Email Automation

Eight React Email templates are fully built and wired to the Resend API:

| Template | Trigger |
| --- | --- |
| inquiry-confirmation | Student submits the apply form |
| admin-notification | New inquiry alert to admin team |
| inquiry-followup | 48-hour follow-up if inquiry status is still “new” |
| consultation-confirmation | Cal.com booking created |
| consultation-reminder | 24h and 1h before scheduled consultation |
| nurture-week1 through nurture-week4 | Weekly nurture email sequence |

Three Supabase Edge Functions are written (not yet deployed) to run as cron jobs:

- send-followups — daily at 9am, sends 48hr follow-up emails

- send-reminders — hourly, sends 24h and 1h consultation reminders

- handle-no-shows — daily, marks no-shows and sends rescue emails

## 1.5 AI Chatbot

- Floating widget on all public pages with open/minimise toggle, unread badge, typing indicator, and quick-reply buttons

- Backend (POST /api/chatbot) uses OpenAI GPT-4o-mini with a custom system prompt trained on MakeoverArena’s services, pricing, and escalation rules

- Rate limited — 30 messages per minute per IP

- Saves conversation history to chat_conversations table in Supabase

## 1.6 Consultation Booking

- /book page — Cal.com iframe embed renders automatically when NEXT_PUBLIC_CALCOM_URL is set; shows clear setup instructions otherwise

- Webhook handler (POST /api/webhooks/calcom) — fully implemented for:

  - BOOKING_CREATED — inserts consultation record, links to existing inquiry by email, updates inquiry status to consultation_booked, sends confirmation email

  - BOOKING_RESCHEDULED — updates date/time in database

  - BOOKING_CANCELLED — marks consultation as cancelled

- HMAC-SHA256 webhook signature verification

## 1.7 Admin Dashboard

Five admin pages are built with live Supabase data queries:

| Page | Features |
| --- | --- |
| Overview (/admin) | KPI cards (inquiries, consultations, conversion rate, active clients), recent inquiries list, upcoming consultations, conversion funnel visualisation |
| Inquiries (/admin/inquiries) | Paginated table (20/page), filter by status/service/priority, total and new-today counts |
| Consultations (/admin/consultations) | Paginated table, filter by status, today/upcoming/completed/no-show stat cards, Join meeting links |
| Analytics (/admin/analytics) | Overview stats, weekly bar chart, conversion funnel, service breakdown, top destinations |
| Settings (/admin/settings) | Team management, email sequences list, integrations panel, notification toggles, company info form |

Admin authentication is fully implemented:

- Login page at /admin/login with branded UI

- HMAC-SHA256 signed session cookie (7-day expiry)

- Proxy middleware intercepts all /admin/* routes — redirects to login if unauthenticated

- Logout button in sidebar clears cookie and redirects

- Credentials controlled by ADMIN_EMAIL and ADMIN_PASSWORD environment variables

## 1.8 Database Schema

All tables are defined in Supabase migration files (ready to push):

| Table | Purpose |
| --- | --- |
| inquiries | All student applications — 30+ columns, indexes, RLS |
| consultations | Booking records linked to inquiries |
| staff_profiles | Admin/consultant/viewer role management |
| email_logs | Full audit trail of every email sent |
| chat_conversations | Chatbot session history |
| analytics_events | Custom event tracking |
| client_profiles | Onboarded client accounts |
| application_tracking | Per-client application progress with stage tracking |
| payments | Payment records per client |

Row Level Security (RLS) is enabled on all tables. Two SQL views (daily_inquiry_stats, service_breakdown) power the analytics dashboard.

## 1.9 Build Quality

- Zero TypeScript errors — clean production build confirmed

- Zero ESLint warnings

- Zod v4 migration completed (breaking API changes handled)

- Supabase type workarounds applied for self-referential types

- proxy.ts (Next.js 16 middleware convention) correctly configured

- Tailwind CSS v4 @import and @theme inline directives applied

# 2. What Remains To Be Done

## 2.1 Critical — Blocks Launch

| Item | Detail |
| --- | --- |
| Push Supabase migrations | supabase db push — without this, no data is stored anywhere |
| Paystack payment integration | PRD core requirement — zero code exists. Needs SDK, payment route, webhook, DB updates |
| Document upload system | PRD core requirement — zero code exists. Needs Supabase Storage bucket, upload UI, admin review |
| Real API credentials | OpenAI, Upstash Redis, Cal.com, GA4 — all placeholder values |

## 2.2 Important — Should Ship at Launch

| Item | Detail |
| --- | --- |
| Client-facing user auth | Student signup/login so the /dashboard shows real data |
| Cal.com account configuration | Set event type, connect webhook, set NEXT_PUBLIC_CALCOM_URL |
| Deploy Supabase Edge Functions | Email cron jobs for follow-ups, reminders, no-show handling |
| Verified sending domain on Resend | Replace onboarding@resend.dev with noreply@makeoverarena.com |
| WhatsApp number | Replace placeholder wa.me/2348000000000 with real business number |
| Vercel production deploy | Push env vars to Vercel, run vercel --prod |
| Custom domain | Point makeoverarena.com to Vercel |

## 2.3 Post-Launch Improvements

| Item | Detail |
| --- | --- |
| Image optimisation | Replace <img> tags with next/image for WebP and lazy loading |
| GA4 custom events | Track form steps, chatbot opens, booking completions |
| Admin search | Search inquiries by name, email, or phone |
| Bulk actions | Assign, status-change, or export multiple inquiries |
| Inquiry detail panel | Side panel with activity timeline and internal notes |
| Calendar view | Month/week view for consultations |
| Consultation follow-up email | Post-consultation template (missing from series) |
| Lighthouse audit | Target 90+ on Performance, Accessibility, SEO |
| Stripe integration | Future global payment option (Phase 3 per PRD roadmap) |

# 3. Four-Week Release Plan

## Week 1 — Infrastructure & Data (Days 1–7)

Goal: The platform can store and retrieve real data end-to-end.

| Day | Task | Owner |
| --- | --- | --- |
| 1 | Get Supabase DB password, run supabase db push, verify all 9 tables created | Dev |
| 1 | Set all real API keys in .env.local: OpenAI, Upstash Redis, GA4 | Dev |
| 2 | Create Upstash Redis account (free tier), update env vars, verify rate limiting active | Dev |
| 2 | Create Cal.com account, configure 30-min free consultation event type, set NEXT_PUBLIC_CALCOM_URL | Dev |
| 3 | Set up Cal.com webhook pointing to /api/webhooks/calcom, set CALCOM_WEBHOOK_SECRET | Dev |
| 3 | Test end-to-end inquiry flow: submit /apply → check Supabase → confirm emails received | Dev |
| 4 | Set ADMIN_PASSWORD to a secure value, test admin login → dashboard → logout | Dev |
| 4 | Verify admin dashboard shows live inquiry data after test submission | Dev |
| 5 | Set up Resend verified sending domain (makeoverarena.com) | Dev |
| 5 | Deploy Supabase Edge Functions (send-followups, send-reminders, handle-no-shows) | Dev |
| 6–7 | Buffer: fix any issues found during testing | Dev |

Week 1 exit criteria: A student can submit the apply form, the record appears in the admin dashboard, and two emails are received (student confirmation + admin alert).

## Week 2 — Payments & Documents (Days 8–14)

Goal: The two critical PRD gaps are closed.

| Day | Task | Owner |
| --- | --- | --- |
| 8 | Create Paystack account, get test API keys | Dev |
| 8 | Install Paystack SDK, create POST /api/payments/initiate route | Dev |
| 9 | Build payment initiation UI — triggered from client dashboard and admin | Dev |
| 9 | Create Paystack webhook handler (POST /api/webhooks/paystack) — verify signature, update payment status in DB | Dev |
| 10 | Connect payment confirmation to email notification | Dev |
| 10 | End-to-end payment test with Paystack test cards | Dev |
| 11 | Configure Supabase Storage bucket (documents) with RLS — clients can only read own files | Dev |
| 11 | Build document upload UI on the client dashboard — file picker, progress indicator, file list | Dev |
| 12 | Build admin document review panel — view uploaded files per client, approve/reject | Dev |
| 13 | Test full document flow: upload → appears in admin → admin approves | Dev |
| 14 | Buffer: fix issues, polish UI | Dev |

Week 2 exit criteria: A client can pay online via Paystack (test mode) and upload documents. Admin can see both.

## Week 3 — Client Auth & Polish (Days 15–21)

Goal: Students have real accounts. The full user journey works.

| Day | Task | Owner |
| --- | --- | --- |
| 15 | Enable Supabase Auth email/password for client-facing signup | Dev |
| 15 | Build /signup page — links from the apply form success screen | Dev |
| 16 | Build /login page for returning clients | Dev |
| 16 | Wire client dashboard (/dashboard) to authenticated user’s data — profile, applications, payments, consultations | Dev |
| 17 | Link inquiry submission to account creation (or prompt after submission) | Dev |
| 17 | Build “forgot password” / password reset flow | Dev |
| 18 | Replace WhatsApp placeholder number with real business number | Dev |
| 18 | Run Lighthouse audit, fix Performance and Accessibility issues | Dev |
| 19 | Replace <img> tags with next/image across all public pages | Dev |
| 19 | Add GA4 custom events: form steps, chatbot open, booking completed | Dev |
| 20–21 | Cross-browser testing (Chrome, Firefox, Safari, Edge), mobile testing (iOS Safari, Android Chrome) | Dev |

Week 3 exit criteria: A student can create an account, submit an inquiry, book a consultation, pay, and upload documents — all tracked under their profile.

## Week 4 — Deployment & Launch (Days 22–30)

Goal: Platform is live at makeoverarena.com.

| Day | Task | Owner |
| --- | --- | --- |
| 22 | Create production Supabase project (separate from dev) | Dev |
| 22 | Run migrations on production Supabase, verify schema | Dev |
| 23 | Add all environment variables to Vercel dashboard | Dev |
| 23 | Run vercel --prod — first production deployment | Dev |
| 24 | Configure custom domain makeoverarena.com on Vercel | Dev |
| 24 | Switch Paystack to live mode, update API keys | Dev |
| 25 | Full smoke test on production: inquiry → consultation → payment → documents | Dev |
| 25 | Set up uptime monitoring (UptimeRobot or Vercel checks) | Dev |
| 26 | Configure weekly Supabase DB backup export | Dev |
| 26 | Verify GA4 receiving live events on production domain | Dev |
| 27–28 | Internal UAT with MakeoverArena team — guided walkthrough of all flows | Client + Dev |
| 29 | Fix any UAT-identified issues | Dev |
| 30 | Launch — announce to existing WhatsApp/Instagram audience | Client |

Week 4 exit criteria: Platform is publicly accessible at makeoverarena.com, all flows work in production, monitoring is active.

# 4. Third-Party Integrations Audit

## 4.1 Resend (Email Service)

| Purpose | All transactional emails: inquiry confirmation, admin alerts, consultation reminders, 4-week nurture sequence |
| --- | --- |
| PRD Requirement | Yes — “Email notifications, consultation reminders, admin alerts” |
| Built | Fully built — 8 React Email templates, shared send utility, email audit log |
| Credentials | Real API key present and working |
| Remaining | Set up verified sending domain (noreply@makeoverarena.com) to replace the default onboarding@resend.dev before launch. Without this, emails may land in spam. |

## 4.2 Supabase (Database & Storage)

| Purpose | All data storage: 9 database tables, Row Level Security, SQL analytics views |
| --- | --- |
| PRD Requirement | Yes — core backend infrastructure |
| Built | Fully built — schema, RLS policies, indexes, migration files |
| Credentials | Real project URL, anon key, and service role key present |
| Remaining | Run supabase db push to apply migrations to the remote database. Configure Supabase Storage bucket for document uploads (Week 2). |

## 4.3 OpenAI (AI Chatbot)

| Purpose | Powers the chatbot widget using GPT-4o-mini with a custom MakeoverArena knowledge base |
| --- | --- |
| PRD Requirement | Not in PRD — added as a value-add feature |
| Built | Fully built — API route, system prompt, escalation logic, conversation persistence, rate limiting |
| Credentials | Placeholder (sk-your-key-here) — chatbot will fail at runtime |
| Remaining | Add a real OpenAI API key. Estimated monthly cost at current usage: $5–20/month. |

## 4.4 Cal.com (Consultation Scheduling)

| Purpose | Free 30-minute consultation booking, automated reminders, calendar sync |
| --- | --- |
| PRD Requirement | Yes — “Calendly or Google Calendar integration” |
| Built | Iframe embed on /book page (renders when URL is set), full webhook handler for booking/rescheduling/cancellation |
| Credentials | Placeholder — NEXT_PUBLIC_CALCOM_URL is empty, CALCOM_API_KEY and CALCOM_WEBHOOK_SECRET are placeholders |
| Remaining | Create Cal.com account, configure the 30-min event type, set the three environment variables. Free plan is sufficient for this use case. |

## 4.5 Upstash Redis (Rate Limiting)

| Purpose | Sliding window rate limiting on the inquiry form (5/hr per IP) and chatbot (30/min per IP) to prevent abuse |
| --- | --- |
| PRD Requirement | Not in PRD — security enhancement |
| Built | Fully built with graceful fallback — if Redis is unavailable, all requests are allowed through |
| Credentials | Placeholder — UPSTASH_REDIS_REST_URL and UPSTASH_REDIS_REST_TOKEN are not set |
| Remaining | Create a free Upstash account, create a Redis database, add the two environment variables. Free tier (10,000 commands/day) is sufficient. |

## 4.6 Google Analytics 4 (Analytics)

| Purpose | Pageview tracking and custom event tracking (form steps, chatbot interactions, booking completions) |
| --- | --- |
| PRD Requirement | Not explicit but implied by success metrics |
| Built | GA4 script injected in root layout with afterInteractive strategy. Custom events not yet instrumented. |
| Credentials | Placeholder measurement ID (G-XXXXXXXXXX) |
| Remaining | Create GA4 property, add real measurement ID. Add custom event calls for form steps, chatbot opens, and booking completions (Week 3). |

## 4.7 Vercel (Deployment)

| Purpose | Hosting, serverless functions, preview deployments, SSL |
| --- | --- |
| PRD Requirement | Not specified — implementation choice |
| Built | Project linked (.vercel/project.json with project ref present) |
| Credentials | Not configured in Vercel dashboard |
| Remaining | Add all environment variables to Vercel dashboard via vercel env add. Run vercel --prod for first production deployment. Configure makeoverarena.com custom domain. |

## 4.8 Paystack (Payments) — NOT BUILT

| Purpose | Online card payments for consultancy service fees — Nigerian and African cards |
| --- | --- |
| PRD Requirement | Yes — explicitly required. Listed as a core deliverable with Stripe as a future option for global expansion |
| Built | Nothing — no SDK installed, no payment routes, no payment UI, no webhook handler |
| Credentials | None |
| Remaining | This is the largest remaining gap. Requires: Paystack account, public/secret API keys, payment initiation endpoint, client-facing payment UI, webhook handler for payment confirmation, database updates on successful payment. Estimated build time: 3–4 days (Week 2 of plan). |

## 4.9 Document Storage — NOT BUILT

| Purpose | Students upload academic transcripts, certificates, and credentials during onboarding |
| --- | --- |
| PRD Requirement | Yes — explicitly required. PRD specifies “Firebase free-tier or equivalent” |
| Built | Nothing — no storage bucket, no upload UI, no admin review interface |
| Credentials | None needed — Supabase Storage is already available within the existing Supabase project |
| Remaining | Configure Supabase Storage bucket with appropriate RLS policies, build file upload component with progress indicator, build admin document review panel. Estimated build time: 2–3 days (Week 2 of plan). |

## 4.10 WhatsApp Business

| Purpose | Customer communication and support channel |
| --- | --- |
| PRD Requirement | Listed as optional |
| Built | WhatsApp button exists on the /book page linking to wa.me/2348000000000 (placeholder number) |
| Credentials | None — no API integration planned |
| Remaining | Replace placeholder phone number with the real MakeoverArena WhatsApp Business number. API integration (for automated messages) is optional and can be addressed in Phase 2. |

## 4.11 Integration Status Summary

| Integration | Provider | PRD Required | Code Status | Credentials |
| --- | --- | --- | --- | --- |
| Email | Resend | Yes | ✅ Complete | ✅ Real key |
| Database | Supabase | Yes | ✅ Complete | ✅ Real (not pushed) |
| AI Chatbot | OpenAI | No | ✅ Complete | ❌ Placeholder |
| Scheduling | Cal.com | Yes | 🔶 Embed + webhook | ❌ Placeholder |
| Rate Limiting | Upstash Redis | No | ✅ Complete | ❌ Placeholder |
| Analytics | Google Analytics 4 | No | 🔶 Pageviews only | ❌ Placeholder |
| Deployment | Vercel | No | 🔶 Linked | ❌ Not configured |
| Payments | Paystack | Yes | ❌ Not built | ❌ None |
| Documents | Supabase Storage | Yes | ❌ Not built | ❌ None |
| WhatsApp | WhatsApp Business | Optional | ⬜ Placeholder link | ❌ None |

# 5. Overall Progress Summary

| Phase | Description | Status | Completion |
| --- | --- | --- | --- |
| 1 | Foundation — Project setup, auth, DB schema | 🔶 Partial | ~95% |
| 2 | Public Website — All marketing pages | ✅ Done | ~95% |
| 3 | Inquiry Form — Multi-step apply form | ✅ Done | ~90% |
| 4 | Email Automation — Templates + Edge Functions | 🔶 Partial | ~75% |
| 5 | AI Chatbot — Widget + API | 🔶 Partial | ~80% |
| 6 | Consultation Booking — Cal.com integration | 🔶 Partial | ~40% |
| 7 | Admin Dashboard — CRM interface | 🔶 Partial | ~75% |
| 8 | Analytics — Tracking + reporting | 🔶 Partial | ~30% |
| 9 | Performance — Optimisation | ☐ Not started | 0% |
| 10 | Security & Compliance | 🔶 Partial | ~75% |
| 11 | Build Quality | ✅ Done | 100% |
| 12 | Deployment & Launch | ☐ Not started | 0% |
| — | Payments (PRD requirement) | ❌ Not built | 0% |
| — | Documents (PRD requirement) | ❌ Not built | 0% |

Overall project completion: ~78%

The remaining 22% is concentrated in three areas: Paystack payments, document uploads, and production deployment — all of which are covered in the 4-week release plan above.